## Sheet1
Procurement Plan / Plan nabave 2014./2015.
IPA2007/HR/16IPO/001-040701/ Procurement plan for Development Of Regional ICT Businsess Incubator Support Network - DORIBIS Network
| Procurement name (ordinal number, procurement name, lot name if applicable) | Procurement value (EUR/HRK)* | Responsible person (Grant Beneficiary or Partner) | Budget line (according to the contract budget) | PT2/ Project Manager | Legal Basis**/Type of procurement procedure*** |  | Type of contract (service/works/supply/other) | 2014 | [6 empty] | 2015
[6 empty] | Croatian Public Procurement Act | Procurement procedures for non purchasing organzations |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 | IPA2007/HR/16IPO/001-040701/WKS/1 - Procurement of Construction works | 299.404,63 EUR/ 2.273.678,76 HRK | Miholjac Entrepreneurial Center / Valent Poslon | 6.1.1 Main construction and craft works 150.770,67; 6.1.2 Hydro-insulation work 18.104,24; 6.1.3 Electric installations 40.426,67; 6.1.4 Mechanical installations 15.151,87; 6.1.5 Construction of access roads 67.133,33; 6.1.6 Air condition 7.817,85 |  | Local Open Tender Procedure |  | works | bar: 2014 7 to 2015 5
2 | IPA2007/HR/16IPO/001-040701/WKS/2 - Procurement of Adaptation works | 88.895,85 EUR/ 675.075,09 HRK | Business incubator BIOS / Jean-Pierre Maričić | 6.2.1 Preparation works 4.323,20; 6.2.2 Plaster works 12.323,33; 6.2.3 Screed layer works 5.693,33; 6.2.4 Insulation works 5.856,00; 6.2.5 Painting and varnishing 5.873,33; 6.2.6 Floor covering works 14.893,33; 6.2.7 Electric installation 14.733,33; 6.1.6 Air condition 25.200,00 |  | Local Open Tender Procedure |  | works | bar: 2014 7 to 2015 2
3 | IPA2007/HR/16IPO/001-040701/SER/1 - Procurement of supervision services for construction works in Donji Miholjac | 6.697,76EUR / 50.862,79 HRK | Miholjac Entrepreneurial Center / Valent Poslon | 5.11. Supervision of construction works 6.697,76 |  | Procedures established by the Beneficiary |  | service | bar: 2014 8 to 2015 6
4 | IPA2007/HR/16IPO/001-040701/SER/2 - Procurement of design and printing visibility and promotions material | 4.425,00 EUR/ 33.603,45 HRK | Miholjac Entrepreneurial Center / Valent Poslon | 5.1.1 Informative leaflet - design 200,00 5.8.1 Visibility material - design 300,00 5.1.2 Informative leaflet - print 1.350,00; 5.8.2 FLAG (300x100) 246,00; 5.8.3 Roll-up panel (Penguin) 260,00; 5.8.4 Table flag 69,00; 5.8.5 Poster (B2 format) 100,00; 5.8.6 Wall panel (B2 format) 250,00; 5.8.7 Pencil 275,00; 5.8.8 Notebook (A5 format) 425,00; 5.8.9 Folder (A4 format) 950,00 |  | Procedures established by the Beneficiary |  | service | bar: 2014 6 to 2014 9
5 | IPA2007/HR/16IPO/001-040701/SER/3 - Procurement of supervision services for adaptation works in Osijek | 2.222,40 EUR / 16.876,90 HRK | Business incubator BIOS / Jean-Pierre Maričić | 5.12. Supervision of adaptation works 2.222,40 |  | Procedures established by the Beneficiary |  | service | bar: 2014 8 to 2015 3
6 | IPA2007/HR/16IPO/001-040701/SER/4 - Procurement of training for mobile developers | 7.250,00EUR / 55.056,50 HRK | Miholjac Entrepreneurial Center / Valent Poslon | 5.7.5.2 Training on ICT support programmmes (Mobile application development) |  | Procedures established by the Beneficiary |  | service | bar: 2014 9 to 2015 10
7 | IPA2007/HR/16IPO/001-040701/SER/5 - Procurement of training of managment and SMEs | 21.600,00EUR/ 164.030,40 HRK | Business incubator BIOS / Jean-Pierre Maričić | 5.7.5.1 Training on ICT support programmmes 5.7.1 Training: Financing options for start-up (5.7.1.1 Trainer fee) 3.000,00; 5.7.2 Trinaing: Business Development and Strategy (5.7.2.1 Trainer fee) 3.000,00; 5.7.3 Training: Business Networking and Investor Relations (5.7.3.1 Trainer fee) 3.000,00; 5.7.4 Training: Investor's perspective (5.7.4.1 Trainer fee) 3.000,00 |  | Procedures established by the Beneficiary |  | service | bar: 2014 11 to 2015 9
8 | IPA2007/HR/16IPO/001-040701/SER/6 - Procurement of travel and accomodation | 31.000,00EUR/ 235.414,00 HRK | Business incubator BIOS / Jean-Pierre Maričić | 5.7.6 Costs of trianing program (London, Berlin - travel and accomodation for participants) 24.000,00; 5.9.5 Presentation of SMEs at specialised international events (5.9.5.1 Travel and accomodaton for participants) 7.000,00 |  | Local Open Tender Procedure |  | service | bar: 2014 9 to 2015 5
9 | IPA2007/HR/16IPO/001-040701/SER/7 - Procurement of exhibition space on CeBIT | 6.000,00EUR/ 45.564,00 HRK | Business incubator BIOS / Jean-Pierre Maričić | 5.9.5.2 Costs of exhibition space |  | Procedures established by the Beneficiary |  | service | bar: 2014 7 to 2015 5
10 | IPA2007/HR/16IPO/001-040701/SER/8 - Procurement of lunch for participants in Donji Miholjac | 2.400,00EUR/ 18.225,60 HRK | Miholjac Entrepreneurial Center / Valent Poslon | 5.7.2.2 Lunch for participants 450,00; 5.7.2.4 Lunch for participants 450,00; 5.7.7 Opening conference 1.500,00 |  | Procedures established by the Beneficiary |  | service
11 | IPA2007/HR/16IPO/001-040701/SER/9 - Procurement of marketing campaign | 13.886,00 EUR/ 103.450,29 HRK | Miholjac Entrepreneurial Center / Valent Poslon | 5.9.1 Specialized live broadcasting on regional TV (30 min) 5.9.2 Radio live broadcasting on regional radio station (30 min) 5.9.3 Adds in the regional newspapers 5.9.4 Intermet marketing camapaign |  | Procedures established by the Beneficiary |  | service
12 | IPA2007/HR/16IPO/001-040701/SER/10 - Procurement of exhibition space on Heureka | 6.000,00EUR/ 45.564,00 HRK | Business incubator BIOS / Jean-Pierre Maričić | 5.9.5.2 Costs of exhibition space |  | Procedures established by the Beneficiary |  | service | bar: 2014 7 to 2015 5
13 | IPA2007/HR/16IPO/001-040701/SER/11 - Procurement of lunch for participants in Osijek | 2.400,00EUR/ 18.225,60 HRK | Business incubator BIOS / Jean-Pierre Maričić | 5.7.2.1 Lunch for participants 450,00; 5.7.2.3 Lunch for participants 450,00; 5.7.8 Closing conference 1.500,00 |  | Procedures established by the Beneficiary |  | service | bar: 2014 11 to 2015 11
14 | IPA2007/HR/16IPO/001-040701/SER/12 - Procurement of knowledge transfer web platform | 30.000,00EUR/ 227.820,00 HRK | Business incubator BIOS / Jean-Pierre Maričić | 5.10 Development of knowledge transfer web platform |  | Local Open Tender Procedure |  | service | bar: 2015 1 to 2015 10
15 | IPA2007/HR/16IPO/001-040701/SUP/1 - Procurement of equipment for Tech park Donji Miholjac | 8.635,00EUR/ 65.574,19HRK | Miholjac Entrepreneurial Center / Valent Poslon | 3.2.2.1 Laptop computer 6.000,00; 3.2.2.2 Desktop computer 400,00; 3.2.2.3 Video projector 550,00; 3.2.2.4 Electric projection screen 200,00; 3.2.2.5 LCD TV 480,00; 3.2.2.6 Digital camera 200,00; 3.2.2.7 Magnetic bord 200,00€ 3.2.2.8 Cork bulletin bord 70,00 3.2.2.9 Audio system 335,00 |  | Procedures established by the Beneficiary |  | supply | bar: 2015 5
16 | IPA2007/HR/16IPO/001-040701/SUP/2 - Procurement of furniture | 39.985,00EUR/ 303.646,10HRK | Business incubator BIOS / Jean-Pierre Maričić | 3.2.1.1 Office desk 1.330,00; 3.2.1.2 Multimedia room desk 1.620,00; 3.2.1.3 Office chair 590,00; 3.2.1.4 Conference chair 885,00; 3.2.1.5 Shelf (wooden) 1.120,00; 3.2.1.6 Office Cabinet 1.800,00; 3.2.3.1 Office chair 4.425,00; 3.2.3.2 Office desk 9.975,00; 3.2.3.3 Office drawer 8.625,00; 3.2.3.4 Office cabinet 6.264,00; 3.2.3.5 Wardrobe cabinet 2.205.00; 3.2.3.6 Reception seating set 1.146,00 |  | Local Open Tender Procedure |  | supply | bar: 2015 5
| * define the procurement value in EUR and HRK (please use exchange rate for June/2014 from InforEur) | 7.5889 | [6 empty] | 2014 7: mark duration of procurement procedure (from invitation to tender/ publication of tender documentation - until contract siganture)
| * *define legal basis marking"x" | [7 empty] | 2014 7: mark contract duration (from contract signature until end of implementation)
*** define the type of procurement procedure according to Annex IV of Grant contract (* International Restricted Tender Procedure; International Open Tender Procedure; Local Open Tender Procedure; Negotiated Procedure, Procedures established by the Beneficiary)

## Sheet2
[10 empty] | datum potpisa ugovora | dobavljač | Planirani mjesec završetka ugovora nabave | Stvarni datum završetka ugovora nabave | Iznos potpisanog ugovora
IPA2007/HR/16IPO/001-040701/WKS/1 - Procurement of Construction works - Nabava građevinskih radova | Nabava radova | ZJN | Otvoreni | Ex-post | 2273678.76 | 2842098.45 | 2014-07-01 | 2014-07-01 | 2014-09-01 | 26.8.2014. | Zitex d.o.o , Campeco j.d.o.o. | 2015-07-01 |  | 2271796.92
IPA2007/HR/16IPO/001-040701/WKS/2 - Procurement of Adaptation works | Nabava radova | ZJN | Otvoreni | Ex-ante | 675075.09 | 843843.8625 | 2014-07-01 | 2014-07-01 | 2014-09-01 | 2015-01-07 | Gradnja d.o.o. | 2015-09-01 | 2015-09-01 | 588.966,03 HRK
IPA2007/HR/16IPO/001-040701/SER/1 - Procurement of supervision services for construction works in Donji Miholjac | Nabava usluga | ZJN | Bagatelna nabava | n/a | 50862.79 | 63578.4875 | 2014-08-01 | nije primjenjivo | 2014-09-01 | 2015-09-22 | Rechner d.o.o | 2015-12-01 |  | 23.000,00 HRK
IPA2007/HR/16IPO/001-040701/SER/2 - Procurement of design and printing visibility and promotions material | Nabava usluga | ZJN | Bagatelna nabava | n/a | 33603.45 | 42004.3125 | 2014-06-01 | nije primjenjivo | 2014-10-01 | 2014-07-02 | Grafo d.o.o. | 2015-09-01 |  | 33346
IPA2007/HR/16IPO/001-040701/SER/3 - Procurement of supervision services for adaptation works in Osijek | Nabava usluga | ZJN | Bagatelna nabava | n/a | 16876.9 | 21096.125 | 2014-07-01 | nije primjenjivo | 2014-09-01 | 2015-01-09 | Trinas projekt d.o.o. | 2015-04-01 |  | 16800
IPA2007/HR/16IPO/001-040701/SER/4 - Procurement of training for mobile developers | Nabava usluga | ZJN | Bagatelna nabava | n/a | 55056.5 | 68820.625 | 2014-10-01 | nije primjenjivo | 2014-11-01 | 2014-09-15 | Mispodino d.o.o. | 2015-11-01 |  | 55000
IPA2007/HR/16IPO/001-040701/SER/5 - Procurement of training of managment and SMEs | Nabava usluga | ZJN | Bagatelna nabava | n/a | 164030.4 | 205038 | 2014-11-01 | N/A | 2014-12-01 | 2015-02-25 | Adriatic advisors | 2015-10-01 |  | 160000
IPA2007/HR/16IPO/001-040701/SER/6 - Procurement of travel and accomodation | Nabava usluga | ZJN | Otvoreni | Ex-ante | 235414 | 294267.5 | 2014-11-01 | Informacija nije dostupna. | 2014-11-01 | 2015-02-25 | Adriatic advisors | 2015-06-01
IPA2007/HR/16IPO/001-040701/SER/7 - Procurement of exhibition space on CeBIT | Nabava usluga | ZJN | Bagatelna nabava | n/a | 45564 | 56955 | 2014-11-01 | nije primjenjivo | 2015-04-01 | Informacija nije dostupna. |  | 2015-06-01
IPA2007/HR/16IPO/001-040701/SER/8 - Procurement of lunch for participants in Donji Miholjac | Nabava usluga | ZJN | Bagatelna nabava | n/a | 18225.6 | 22782 | 2014-11-01 | nije primjenjivo | 2014-07-01 | Informacija nije dostupna. |  | 2015-12-01
IPA2007/HR/16IPO/001-040701/SER/9 - Procurement of promotional activities - Marketing campaign | Nabava usluga | ZJN | Bagatelna nabava | n/a | 105379.95 | 131724.9375 | 2014-11-01 | nije primjenjivo | 2014-07-01 | 10.2.2015. | DUGA d.o.o. | 2015-12-01 |  | 105000
IPA2007/HR/16IPO/001-040701/SER/10 - Procurement of exhibition space on Heureka | Nabava usluga | ZJN | Bagatelna nabava | n/a | 45564 | 56955 | 2014-11-01 | nije primjenjivo | 2015-05-01 | Informacija nije dostupna. |  | 2015-06-01
IPA2007/HR/16IPO/001-040701/SER/11 - Procurement of lunch for participants in Osijek | Nabava usluga | ZJN | Bagatelna nabava | n/a | 18225.6 | 22782 | 2014-11-01 | nije primjenjivo | 2015-03-01 | Informacija nije dostupna. |  | 2015-12-01
IPA2007/HR/16IPO/001-040701/SER/12 - Procurement of knowledge transfer web platform | Nabava usluga | ZJN | Otvoreni | n/a | 227820 | 284775 | 2015-05-01 | Informacija nije dostupna. | 2015-02-01 | Informacija nije dostupna. |  | 2015-11-01
IPA2007/HR/16IPO/001-040701/SUP/1 - Procurement of equipment for Tech park Donji Miholjac | Nabava roba | ZJN | Bagatelna nabava | n/a | 65574.19 | 81967.7375 | 2015-05-01 | nije primjenjivo | 2016-06-01 |  |  | 2015-07-01
IPA2007/HR/16IPO/001-040701/SUP/2 - Procurement of furniture | Nabava roba | ZJN | Otvoreni | Ex-post | 303646.1 | 379557.625 | 2016-05-01 |  | 2016-06-01 |  |  | 2015-07-01